## Deliverables
CDRL | Title | POC | Status | Location on Redmine | Notes
A001 | CDPM/PCIDS Briefing |  | OBE | N/A | CDPM removed, support Gov ERB efforts
A001 | IC&T Briefing |  | OBE | N/A | No graduation test event
A003 | Program Management Plan | Foreman | complete | N/A
A006 | Work Breakdown Structure | Foreman | complete | N/A
A008 | Integrated Program Management Report | Foreman | complete | N/A
A010 | Initial Requirements Trace (RVTM) (update throughout project) |  | complete |  | Modified: Prepared high-level requirements documentation
A010 | Capability Design for PCIDS Board |  | OBE | N/A
A010 | Final Report with all deliverables | Foreman |  | N/A
A010 | Final SLOC Report (should be complete for Final Report) | Collar |  |  | SLOC for each algorithm
A015 | Computer End Item Documentation (all software…) | Dyer |  |  | Code and documentation
A017 | Software Installation Plan | Dyer
A020 | System/Subsystem Design Description for APX | Dyer |  |  | Algorithms documented separately
A023 | Final Software Design Description (1 each for SLAP, SLIP) |  | OBE | N/A | No software development
A024 | Final Interface Design Description | Dyer
A026 | Software Test Plan for APX | Stedman | complete |  | Initial file system test
A027 | Software Test Description for APX | Stedman | complete |  | Initial file system test
A028 | Software Test Report | Stedman | complete |  | Initial file system test
A030 | Software Version Description for APX | Dyer |  |  | Modified to describe setup documentation, versioning
A031 | Software User Manual for APX | Stedman |  |  | Modified to maintenance procedures
A033 | Test Procedure for APX | Stedman | complete |  | Initial file system test
A036 | Training Program Development and Management Plan | Neill | complete
A043 | Training Conduct Support Document for APX | Neill | OBE | N/A | Limited to maintenance training, not needed as early
A049 | COTS Manuals and Associated Supplemental Data | Stedman |  |  | No COTS or licenses, provide for "new" items (InfiniBand)